## Executive Overview
OVALENS: CAPSTONE MASTER FEATURE & ENDPOINT CHECKLIST
Foundation University (CCS) • Team DevIn • DSRM + Agile Framework • Two-Tier Agent Architecture
| Total Items |  | Completed [Done] |  | In Progress | Pending Backlog
Subsystem Domain | Scope & Description | Total Tasks | Done | Completion %
Backend REST API | All FastAPI routers: Auth, Batches, Scans, Analytics, Reports, Settings, Users
Edge CV & Sorter App | Camera grabber, YOLOv8 ONNX, SQLite WAL, cradle tracker, CustomTkinter 60 FPS
Dashboard Web Portal | React 18 + Vite + TS: Tray matrix, batches, analytics, user admin, audit logs
Firmware & Hardware | ESP32 Dev Module, optical interrupts, stepper indexed transport, servo diverters
AI Model & Dataset | 3,000+ Itik Pinas dataset, 70/15/15 split, training, ONNX FP16 slim, benchmarks
Research & Docs | Capstone manuscript (Chapters 1-6), APA citations, thesis defense preparation
Global Automated Workflow Rules:
1. Two-Tier Agent Architecture: Antigravity orchestrates, plans, audits, and commits; Codex implements features and tests.
2. Automated Quality Gate: Every feature MUST pass backend pytest (13 tests), edge pytest (8 tests), and dashboard build.
3. Automated Checklist Sync: Running 'python scripts/verify_and_commit.py --task <TASK_ID> -m "..."' marks the item Done here and in PROJECT_PLAN.md.
4. Strict Architectural Tenets: Zero Firebase (100% FastAPI+PostgreSQL), offline SQLite WAL at edge, 3 biological classes, FU branding (#800000).

## Master Checklist
Task ID | DSRM Phase | Subsystem | Feature / Endpoint | Technical Specification & Acceptance Criteria | Diagram Reference | Role | Status | Priority | Automated Test / Verification
TASK-DOC-01 | Phase 1: Planning | Docs & Plan | Authentic Manuscript Integration | Parse DevIn (2026).md into Chapters 1-6 with 15 APA 7 citations and Title/Approval Sheet | Manuscript 00-06 | Antigravity | Done | P0 - Critical | docs/manuscript/*.md review
TASK-DOC-02 | Phase 1: Planning | Docs & Plan | Import & Catalog Academic Diagrams | Embed and convert IPO Matrix, DSRM Methodology, System Flowchart, and Use Case diagrams (.drawio & .html) | All 4 Diagrams | Antigravity | Done | P0 - Critical | docs/diagrams catalog audit
TASK-DOC-03 | Phase 1: Planning | Docs & Plan | Two-Tier Agent Workflow & Quality Gate | Establish Antigravity + Codex partnership, PROJECT_PLAN.md, CHANGELOG.md, and verify_and_commit.py | PROJECT_PLAN.md | Antigravity | Done | P0 - Critical | python scripts/verify_and_commit.py
TASK-NEW-SCOPE-01 | Phase 4: Development | Cross-System | Day 10 Binary Domain Refactor | Standardize backend, edge, dashboard, firmware, tests, and docs on Day 10 with FERTILE/INFERTILE outcomes | System-wide contract | Codex | Done | P0 - Critical | pytest + npm.cmd run build
TASK-BE-AUTH-01 | Phase 4C: Backend | Backend API | POST /api/v1/auth/login | JWT authentication endpoint with bcrypt password verification and role extraction | Use Case: Worker | Codex | Done | P0 - Critical | test_login_and_me
TASK-BE-AUTH-02 | Phase 4C: Backend | Backend API | GET /api/v1/auth/me | Retrieve current authenticated user profile, permissions, and active status | Use Case: Worker | Codex | Done | P0 - Critical | test_login_and_me
TASK-BE-AUTH-03 | Phase 4C: Backend | Backend API | POST /api/v1/auth/register | Account registration endpoint with default Candling Worker role | Use Case: Admin | Codex | Done | P1 - High | test_rbac_and_admin_security_protections
TASK-BE-USR-01 | Phase 4C: Backend | Backend API | GET /api/v1/users | List all system users with role filters (Worker, Supervisor, Admin) | Use Case: Admin | Codex | Done | P1 - High | test_rbac_and_admin_security_protections
TASK-BE-USR-02 | Phase 4C: Backend | Backend API | POST /api/v1/users | Admin user creation endpoint with RBAC role assignment | Use Case: Admin | Codex | Done | P1 - High | test_rbac_and_admin_security_protections
TASK-BE-USR-03 | Phase 4C: Backend | Backend API | PATCH /api/v1/users/{id}/status | Toggle user active/deactivated state to revoke credentials | Use Case: Admin | Codex | Done | P1 - High | test_rbac_and_admin_security_protections
TASK-BE-USR-04 | Phase 4C: Backend | Backend API | PATCH /api/v1/users/me/profile | Allow authenticated user to update their display name and email | Use Case: Worker | Codex | Done | P2 - Medium | test_user_profile_and_password_change_flow
TASK-BE-USR-05 | Phase 4C: Backend | Backend API | PATCH /api/v1/users/me/password | Secure password change with old password verification | Use Case: Worker | Codex | Done | P1 - High | test_user_profile_and_password_change_flow
TASK-BE-BAT-01 | Phase 4C: Backend | Backend API | GET /api/v1/batches | List incubation batches with status and genetic group filters | Use Case: Supervisor | Codex | Done | P0 - Critical | test_list_batches
TASK-BE-BAT-02 | Phase 4C: Backend | Backend API | GET /api/v1/batches/active | Retrieve currently active incubator batches needing candling inspection | Use Case: Supervisor | Codex | Done | P0 - Critical | test_list_batches
TASK-BE-BAT-03 | Phase 4C: Backend | Backend API | POST /api/v1/batches | Create new incubation batch specifying breed (Itim/Khaki/Kayumanggi) and egg count | Use Case: Supervisor | Codex | Done | P0 - Critical | test_batch_analytics_and_milestones
TASK-BE-BAT-04 | Phase 4C: Backend | Backend API | GET /api/v1/batches/{id} | Get detailed batch record with tray matrix slots and current milestone | Use Case: Supervisor | Codex | Done | P0 - Critical | test_batch_analytics_and_milestones
TASK-BE-BAT-05 | Phase 4C: Backend | Backend API | GET /api/v1/batches/{id}/analytics | Incubation analytics: fertility rate, mortality curve, penoy salvage total | Use Case: Supervisor | Codex | Done | P0 - Critical | test_batch_analytics_and_milestones
TASK-BE-BAT-06 | Phase 4C: Backend | Backend API | GET /api/v1/batches/{id}/forecast | Hatch yield forecast based on the Day 10 fertility rate | Use Case: Supervisor | Codex | Done | P1 - High | test_hatch_yield_forecast_and_backup_service
TASK-BE-BAT-07 | Phase 4C: Backend | Backend API | PUT /api/v1/batches/{id} | Update batch metadata, notes, and incubator chamber ID | Use Case: Supervisor | Codex | Done | P1 - High | test_batch_analytics_and_milestones
TASK-BE-BAT-08 | Phase 4C: Backend | Backend API | POST /api/v1/batches/{id}/advance-stage | Advance lifecycle: Setting -> Day 10 -> Hatched -> Completed | Use Case: Supervisor | Codex | Done | P0 - Critical | test_batch_analytics_and_milestones
TASK-BE-BAT-09 | Phase 4C: Backend | Backend API | POST /api/v1/batches/{id}/finalize-hatch | Close batch lifecycle and record final hatchling count on Day 28 | Use Case: Supervisor | Codex | Done | P1 - High | test_batch_analytics_and_milestones
TASK-BE-BAT-10 | Phase 4C: Backend | Backend API | GET /api/v1/batches/{id}/summary | Comprehensive batch summary DTO for compliance and audit archiving | Use Case: Supervisor | Codex | Done | P1 - High | test_batch_analytics_and_milestones
TASK-BE-BAT-11 | Phase 4C: Backend | Backend API | DELETE /api/v1/batches/{id} | Soft-delete or purge batch (Admin only protection) | Use Case: Admin | Codex | Done | P2 - Medium | test_rbac_and_admin_security_protections
TASK-BE-BAT-12 | Phase 4C: Backend | Backend API | POST /api/v1/batches/check-milestones | Automated background cron to flag batches reaching Day 10, 18, 25 | System Flowchart | Codex | Done | P1 - High | test_batch_analytics_and_milestones
TASK-BE-SES-01 | Phase 4C: Backend | Backend API | GET /api/v1/sessions | List all active and completed edge candling sorting sessions | Use Case: Worker | Codex | Done | P0 - Critical | test_api.py
TASK-BE-SES-02 | Phase 4C: Backend | Backend API | POST /api/v1/sessions | Start new candling session linked to batch and edge sorter device ID | Use Case: Worker | Codex | Done | P0 - Critical | test_api.py
TASK-BE-SES-03 | Phase 4C: Backend | Backend API | GET /api/v1/sessions/{id} | Get Day 10 progress: total, fertile, and infertile counts | Use Case: Worker | Codex | Done | P0 - Critical | test_api.py
TASK-BE-SES-04 | Phase 4C: Backend | Backend API | PUT /api/v1/sessions/{id}/end | Conclude candling session and trigger batch analytics recalculation | Use Case: Worker | Codex | Done | P0 - Critical | test_api.py
TASK-BE-SCN-01 | Phase 4C: Backend | Backend API | POST /api/v1/scans/sync | Idempotent batch scan sync with ON CONFLICT (scan_id) DO NOTHING | System Flowchart | Codex | Done | P0 - Critical | test_analytics_overview
TASK-BE-SCN-02 | Phase 4C: Backend | Backend API | POST /api/v1/scans/upload-image | Upload high-res candling frame image associated with scan ID | System Flowchart | Codex | Done | P1 - High | test_api.py
TASK-BE-SCN-03 | Phase 4C: Backend | Backend API | GET /api/v1/scans | Query historical scans with batch_id, stage, class, date filters | Use Case: Supervisor | Codex | Done | P0 - Critical | test_api.py
TASK-BE-SCN-04 | Phase 4C: Backend | Backend API | GET /api/v1/scans/{id} | Retrieve single scan record with confidence, bounding box, image URI | Use Case: Supervisor | Codex | Done | P1 - High | test_api.py
TASK-BE-SCN-05 | Phase 4C: Backend | Backend API | PATCH /api/v1/scans/{id}/override | Human-in-the-loop classification override with audit trail logging | System Flowchart Node 10 | Codex | Done | P0 - Critical | test_human_in_the_loop_override_audit_logging
TASK-BE-ANL-01 | Phase 4C: Backend | Backend API | GET /api/v1/analytics/overview | Aggregated hatchery statistics (total eggs, fertility rate, cull rate) | Use Case: Supervisor | Codex | Done | P0 - Critical | test_analytics_overview
TASK-BE-ANL-02 | Phase 4C: Backend | Backend API | GET /api/v1/analytics/breed-comparison | Disaggregated analytics comparing IP-Itim vs IP-Khaki vs IP-Kayumanggi | Methodology 3.1 | Codex | Done | P1 - High | test_analytics_overview
TASK-BE-ANL-03 | Phase 4C: Backend | Backend API | GET /api/v1/analytics/mortality-trends | Longitudinal mortality tracking across batches and candling stages | Use Case: Supervisor | Codex | Done | P1 - High | test_mortality_progression
TASK-BE-ANL-04 | Phase 4C: Backend | Backend API | GET /api/v1/analytics/mortality-progression | Day 10 cull analysis by breed | Methodology 3.1 | Codex | Done | P1 - High | test_mortality_progression
TASK-BE-ANL-05 | Phase 4C: Backend | Backend API | GET /api/v1/analytics/economic-yield | Day 10 Penoy salvage revenue (Count * P14.00) & thermal energy savings | AGENTS.md Tenet 3 | Codex | Done | P0 - Critical | test_analytics_economic_yield
TASK-BE-REP-01 | Phase 4C: Backend | Backend API | GET /api/v1/reports/batch/{id}/csv | Export CSV spreadsheet containing detailed scan log for batch | Use Case: Supervisor | Codex | Done | P1 - High | test_pdf_and_csv_reports
TASK-BE-REP-02 | Phase 4C: Backend | Backend API | GET /api/v1/reports/batch/{id}/pdf | Generate official Foundation University formatted PDF compliance report | Use Case: Supervisor | Codex | Done | P0 - Critical | test_pdf_and_csv_reports
TASK-BE-DEV-01 | Phase 4C: Backend | Backend API | GET /api/v1/devices | List registered edge sorter hardware rigs with online/offline status | Use Case: Admin | Codex | Done | P1 - High | test_api.py
TASK-BE-DEV-02 | Phase 4C: Backend | Backend API | POST /api/v1/devices/register | Register new ESP32 / Raspberry Pi edge node with MAC & station ID | Use Case: Admin | Codex | Done | P1 - High | test_api.py
TASK-BE-DEV-03 | Phase 4C: Backend | Backend API | POST /api/v1/devices/{id}/heartbeat | Edge node heartbeat ping transmitting status, temperature, and FPS | Use Case: Admin | Codex | Done | P1 - High | test_api.py
TASK-BE-SET-01 | Phase 4C: Backend | Backend API | GET /api/v1/settings | Fetch system settings (penoy price P14, confidence threshold, sync interval) | Use Case: Admin | Codex | Done | P1 - High | test_settings_endpoint
TASK-BE-SET-02 | Phase 4C: Backend | Backend API | PUT /api/v1/settings | Update system settings with admin validation | Use Case: Admin | Codex | Done | P1 - High | test_settings_endpoint
TASK-BE-SET-03 | Phase 4C: Backend | Backend API | POST /api/v1/settings/backups/create | Trigger compressed JSON.GZ snapshot of PostgreSQL database | AGENTS.md Tenet 1 | Codex | Done | P1 - High | test_hatch_yield_forecast_and_backup_service
TASK-BE-SET-04 | Phase 4C: Backend | Backend API | GET /api/v1/settings/backups | List available database backup archive files | Use Case: Admin | Codex | Done | P2 - Medium | test_hatch_yield_forecast_and_backup_service
TASK-BE-SET-05 | Phase 4C: Backend | Backend API | GET /api/v1/settings/backups/{file}/download | Secure endpoint to download encrypted database backup | Use Case: Admin | Codex | Done | P2 - Medium | test_hatch_yield_forecast_and_backup_service
TASK-BE-AUD-01 | Phase 4C: Backend | Backend API | GET /api/v1/audit_logs | Query immutable system audit trail with user and timestamp filters | Use Case: Admin | Codex | Done | P0 - Critical | test_human_in_the_loop_override_audit_logging
TASK-EDGE-CAM-01 | Phase 4B: Edge App | Edge CV | Multi-Threaded Circular Frame Grabber | Thread 1: OpenCV DirectShow/V4L2 continuous circular buffer drain | AGENTS.md Edge | Codex | Done | P0 - Critical | test_camera_mock_generation_and_lifecycle
TASK-EDGE-CAM-02 | Phase 4B: Edge App | Edge CV | Camera Disconnect Recovery & Mock Mode | Auto-reconnect USB camera and generate mock frames for offline dev | AGENTS.md Edge | Codex | Done | P1 - High | test_camera_mock_generation_and_lifecycle
TASK-EDGE-AI-01 | Phase 4B: Edge App | Edge CV | ONNX Runtime FP16 Inference Engine | Thread 2: ONNX Runtime execution provider running quantized YOLOv8 | System Flowchart Node 8 | Codex | Done | P0 - Critical | test_inference_engine_and_latency_benchmark
TASK-EDGE-AI-02 | Phase 4B: Edge App | Edge CV | Geometric Aspect-Ratio & Centering Gate | Enforce 0.65 <= Aspect Ratio <= 1.45 to prevent classifying non-egg objects | AGENTS.md Edge | Codex | Done | P1 - High | test_candling_heuristics_and_vascularization
TASK-EDGE-AI-03 | Phase 4B: Edge App | Edge CV | Model Cache Warmup Routine | Execute 3 dummy passes on startup to eliminate first-frame latency spikes | AGENTS.md Edge | Codex | Done | P1 - High | test_inference_engine_and_latency_benchmark
TASK-EDGE-HEU-01 | Phase 4B: Edge App | Edge CV | HSV Candling Luminance Analyzer | Analyze internal light transmission across yolk/albumin regions | System Flowchart Node 7 | Codex | Done | P1 - High | test_candling_heuristics_and_vascularization
TASK-EDGE-HEU-02 | Phase 4B: Edge App | Edge CV | Vascular Vein & Blood Ring Heuristics | Auxiliary edge detector verifying spider blood veins vs necrotic ring | System Flowchart Node 8 | Codex | Done | P1 - High | test_candling_heuristics_and_vascularization
TASK-EDGE-DB-01 | Phase 4B: Edge App | Edge CV | Local SQLite WAL Mode Store | Thread 4: Local scan persistence with PRAGMA journal_mode = WAL; | AGENTS.md Edge | Codex | Done | P0 - Critical | test_local_sqlite_wal_and_queue_diagnostics
TASK-EDGE-DB-02 | Phase 4B: Edge App | Edge CV | Unsynced Scan FIFO Queue Manager | Track unsynced scans and handle exponential backoff retry | AGENTS.md Edge | Codex | Done | P0 - Critical | test_local_sqlite_wal_and_queue_diagnostics
TASK-EDGE-SYN-01 | Phase 4B: Edge App | Edge CV | Background REST HTTP Sync Worker | Non-blocking background HTTP client transmitting batches of 50 scans | System Flowchart Node 13 | Codex | Done | P0 - Critical | test_sync_worker_diagnostics
TASK-EDGE-SYN-02 | Phase 4B: Edge App | Edge CV | Local CSV Session Exporter | Emergency offline CSV exporter saving session records to local USB drive | AGENTS.md Offline | Codex | Done | P1 - High | test_csv_session_export
TASK-EDGE-SER-01 | Phase 4B: Edge App | Edge CV | PySerial ESP32 UART Driver | Thread 3: Non-blocking serial worker communicating at 115200 baud | System Flowchart Node 17 | Codex | Done | P0 - Critical | test_esp32_serial_mock_and_motor_commands
TASK-EDGE-SER-02 | Phase 4B: Edge App | Edge CV | Serial Mock Driver for Hardware-Free Dev | Simulate ESP32 optical triggers and servo responses in unit tests | AGENTS.md Firmware | Codex | Done | P1 - High | test_esp32_serial_mock_and_motor_commands
TASK-EDGE-TRK-01 | Phase 4B: Edge App | Edge CV | Cradle Tracking FIFO Queue | Maintain cradle queue mapping cradle_id from image station to sorting gate | System Flowchart Node 5,11 | Codex | Backlog | P0 - Critical | test_cradle_tracking_queue.py
TASK-EDGE-TRK-02 | Phase 4B: Edge App | Edge CV | Conveyor Index Resynchronization Handler | Pause conveyor and alert operator if physical cradle index drifts | System Flowchart Node 15,16 | Codex | Backlog | P1 - High | test_cradle_resync_handler.py
TASK-EDGE-REV-01 | Phase 4B: Edge App | Edge CV | Manual Review Fallback State Machine | Trigger manual review flag when confidence < 0.75 or egg uncentered | System Flowchart Node 9,10 | Codex | Backlog | P0 - Critical | test_manual_review_fallback.py
TASK-EDGE-UI-01 | Phase 4B: Edge App | Edge CV | CustomTkinter 60 FPS Operator Desktop UI | Main Thread: CustomTkinter operator GUI with Foundation University theme | Use Case: Worker | Codex | Done | P0 - Critical | Desktop UI smoke launch
TASK-EDGE-UI-02 | Phase 4B: Edge App | Edge CV | Live Candling Video Viewport | Smooth video rendering canvas with overlay bounding box and class tag | Use Case: Worker | Codex | Done | P0 - Critical | Desktop UI verification
TASK-EDGE-UI-03 | Phase 4B: Edge App | Edge CV | Real-Time Session Statistics Counters | Live counters for Fertile, Infertile, and Manual Review | Use Case: Worker | Codex | Done | P1 - High | Desktop UI verification
TASK-EDGE-UI-04 | Phase 4B: Edge App | Edge CV | Interactive Manual Override Dialog Modal | Modal popup enabling operator to inspect flagged egg and confirm class | System Flowchart Node 10 | Codex | Backlog | P0 - Critical | Desktop UI modal test
TASK-EDGE-UI-05 | Phase 4B: Edge App | Edge CV | Conveyor Pause & Emergency Stop Controls | Instant physical rig pause and serial E-STOP command dispatch | System Flowchart Node 16 | Codex | Done | P1 - High | Desktop UI verification
TASK-DASH-PG-01 | Phase 4D: Dashboard | Dashboard | LoginPage.tsx with JWT Auth | Login view with Foundation University maroon branding and token persistence | Use Case: Worker | Codex | Done | P0 - Critical | npm.cmd run build
TASK-DASH-PG-02 | Phase 4D: Dashboard | Dashboard | OverviewPage.tsx Real-Time KPI Cards | High-level summary of active batches, fertility %, and today's sorting volume | Use Case: Supervisor | Codex | Done | P0 - Critical | npm.cmd run build
TASK-DASH-PG-03 | Phase 4D: Dashboard | Dashboard | BatchesPage.tsx Lifecycle Management | Table of all batches, Day 10 stage advancement, and hatch closure | Use Case: Supervisor | Codex | Done | P0 - Critical | npm.cmd run build
TASK-DASH-PG-04 | Phase 4D: Dashboard | Dashboard | ScanExplorerPage.tsx Visual Search | Filterable grid of historical scan captures with image lightbox inspection | Use Case: Supervisor | Codex | Done | P1 - High | npm.cmd run build
TASK-DASH-PG-05 | Phase 4D: Dashboard | Dashboard | AnalyticsPage.tsx Multi-Chart Suite | Recharts visualizer for mortality curves, breed comparisons, and Penoy revenue | Use Case: Supervisor | Codex | Done | P0 - Critical | npm.cmd run build
TASK-DASH-PG-06 | Phase 4D: Dashboard | Dashboard | RecordsPage.tsx Audit Archive | Historical scan and session records table with one-click CSV/PDF download | Use Case: Supervisor | Codex | Done | P1 - High | npm.cmd run build
TASK-DASH-PG-07 | Phase 4D: Dashboard | Dashboard | DevicesPage.tsx Hardware Monitor | Live cards showing connected Raspberry Pi and ESP32 sorter rigs | Use Case: Admin | Codex | Done | P1 - High | npm.cmd run build
TASK-DASH-PG-08 | Phase 4D: Dashboard | Dashboard | ModelsPage.tsx MLOps Registry | View deployed YOLOv8 ONNX model version, latency benchmarks, thresholds | Use Case: Admin | Codex | Done | P1 - High | npm.cmd run build
TASK-DASH-PG-09 | Phase 4D: Dashboard | Dashboard | UsersPage.tsx User Administration | Admin table for managing operator, supervisor, and administrator accounts | Use Case: Admin | Codex | Done | P0 - Critical | npm.cmd run build
TASK-DASH-PG-10 | Phase 4D: Dashboard | Dashboard | AuditLogsPage.tsx Security Trail | Chronological table of all system events, login attempts, and overrides | Use Case: Admin | Codex | Done | P0 - Critical | npm.cmd run build
TASK-DASH-PG-11 | Phase 4D: Dashboard | Dashboard | SettingsPage.tsx System Configuration | Configure Penoy price (P14), confidence thresholds, and DB backup downloads | Use Case: Admin | Codex | Done | P1 - High | npm.cmd run build
TASK-DASH-CP-01 | Phase 4D: Dashboard | Dashboard | Incubation Tray Matrix (42 Slots A1-F7) | Interactive SVG grid showing physical incubator tray slot occupancy and status | Use Case: Supervisor | Codex | Done | P0 - Critical | npm.cmd run build
TASK-DASH-CP-02 | Phase 4D: Dashboard | Dashboard | Interactive Penoy Economic Calculator | Widget computing Day 10 salvage income based on P14.00/egg price | AGENTS.md Tenet 3 | Codex | Done | P1 - High | npm.cmd run build
TASK-DASH-CP-03 | Phase 4D: Dashboard | Dashboard | Breed Filter: IP-Itim, Khaki, Kayumanggi | Dropdown to isolate metrics by pure line vs commercial hybrid | Methodology 3.1 | Codex | Done | P1 - High | npm.cmd run build
TASK-DASH-CP-04 | Phase 4D: Dashboard | Dashboard | Day 10 Filter | Filter analytics for the single Day 10 checkpoint | Methodology 3.1 | Codex | Done | P1 - High | npm.cmd run build
TASK-DASH-CP-05 | Phase 4D: Dashboard | Dashboard | Dark / Light Mode Theme System | TailwindCSS theme switcher with FU Maroon (#800000) accents | AGENTS.md FU Brand | Codex | Done | P2 - Medium | npm.cmd run build
TASK-FW-INT-01 | Phase 4A: Firmware | Firmware | Optical Sensor Hardware Interrupt | ESP32 GPIO 14 optical beam-break edge detection interrupt | System Flowchart | Codex | Done | P0 - Critical | esp32_actuator.ino review
TASK-FW-INT-02 | Phase 4A: Firmware | Firmware | 600ms Hardware Optical Debounce Lockout | Non-blocking timer lockout preventing false double-triggers on single egg | AGENTS.md Firmware | Codex | Done | P0 - Critical | esp32_actuator.ino review
TASK-FW-LED-01 | Phase 4A: Firmware | Firmware | Candling Strobe LED Driver Relay | GPIO 19 strobe trigger synchronized with camera exposure | System Flowchart Node 7 | Codex | Done | P1 - High | esp32_actuator.ino review
TASK-FW-SER-01 | Phase 4A: Firmware | Firmware | Non-Blocking Serial UART Command Parser | Buffer incoming 115200 baud UART bytes without delay() calls | AGENTS.md Firmware | Codex | Done | P0 - Critical | esp32_actuator.ino review
TASK-FW-SER-02 | Phase 4A: Firmware | Firmware | Serial ACK / NACK Status Protocol | Transmit acknowledgement packets upon command execution to edge driver | System Flowchart Node 3 | Codex | Backlog | P1 - High | Serial loopback test
TASK-FW-STP-01 | Phase 4A: Firmware | Firmware | Stepper Pocket-Conveyor Transport Routine | Indexed step timing to advance pocket conveyor one cradle at a time | System Flowchart Node 6,14 | Codex | Backlog | P0 - Critical | Firmware bench test
TASK-FW-SRV-01 | Phase 4A: Firmware | Firmware | Servo Gate 1 (Fertile Release) | Actuate servo diverter for Fertile eggs into cushioned incubation tray | System Flowchart Node 18 | Codex | Done | P0 - Critical | esp32_actuator.ino review
TASK-FW-SRV-02 | Phase 4A: Firmware | Firmware | Servo Gate 2 (Infertile / Penoy Salvage) | Actuate servo diverter for Day 10 Penoy salvage sale (@ P14.00) | System Flowchart Node 19 | Codex | Backlog | P0 - Critical | Firmware bench test
TASK-FW-KIN-01 | Phase 4A: Firmware | Firmware | Kinematic Actuation Delay Timer | Calculate Delta-t = D / v = 25cm / 12.5cm/s = 2000ms delay before servo firing | Methodology 3.4 | Codex | Done | P0 - Critical | esp32_actuator.ino review
TASK-AI-DS-01 | Phase 2: Dataset | AI & Data | Dataset 70/15/15 Stratification Pipeline | Partition 3,000+ candling images into 70% Train, 15% Val, 15% Test | IPO Matrix / Meth | Codex | Backlog | P0 - Critical | test_dataset_stratification.py
TASK-AI-DS-02 | Phase 2: Dataset | AI & Data | Whole-Egg YOLO Bounding Box Validator | Verify YOLO darknet format [class_id, x, y, w, h] enclosing whole egg | IPO Matrix | Codex | Backlog | P1 - High | test_annotation_bounds.py
TASK-AI-DS-03 | Phase 2: Dataset | AI & Data | Candling Transillumination Augmentations | HSV luminance jitter (V +/-20%) and +/-15 deg rotation pipeline | Chapter 3.2 | Codex | Backlog | P2 - Medium | test_augmentation_visuals.py
TASK-AI-DS-04 | Phase 2: Dataset | AI & Data | Dataset Distribution Summary Exporter | Generate automated Markdown and LaTeX tables of egg counts for manuscript | Chapter 3.2 | Codex | Backlog | P2 - Medium | export_dataset_table.py
TASK-AI-TRN-01 | Phase 3: AI Vision | AI & Data | Ultralytics YOLOv8 Training Script | Implement model training pipeline with CIoU + BCE + DFL loss functions | Methodology 3.3 | Codex | Backlog | P1 - High | train_yolov8.py smoke test
TASK-AI-OPT-01 | Phase 3: AI Vision | AI & Data | ONNX FP16 Slim Export & Half-Precision Graph | Convert PyTorch weights to ONNX FP16 slim graph for edge inference | AGENTS.md Tenet 3 | Codex | Done | P0 - Critical | export_onnx.py check
TASK-AI-OPT-02 | Phase 3: AI Vision | AI & Data | Production Weights 'edge/models/weights/best.onnx' | Verified production ONNX FP16 weights ready for edge execution | AGENTS.md Tenet 3 | Codex | Done | P0 - Critical | test_inference_engine_and_latency_benchmark
TASK-AI-LAT-01 | Phase 3: AI Vision | AI & Data | Edge Inference Latency Benchmark (<=200ms) | Benchmark inference latency ensuring <= 200 ms SLA on edge hardware | Chapter 1 Objectives | Codex | Done | P0 - Critical | test_inference_engine_and_latency_benchmark
TASK-AI-EVL-01 | Phase 3: AI Vision | AI & Data | Breed Subgroup Metric Evaluator | Compute Precision, Recall, F1, mAP for IP-Itim, Khaki, and Kayumanggi | IPO Matrix | Codex | Backlog | P1 - High | test_subgroup_metrics.py
TASK-AI-EVL-02 | Phase 3: AI Vision | AI & Data | Day 10 Subgroup Metric Evaluator | Compute Precision, Recall, F1, and mAP across Day 10 cohorts | IPO Matrix | Codex | Backlog | P1 - High | test_subgroup_metrics.py
TASK-AI-EVL-03 | Phase 3: AI Vision | AI & Data | 2-Class Confusion Matrix & PR Curve Generator | Generate Fertile/Infertile metrics for Chapter 4 | Chapter 4 Manuscript | Codex | Backlog | P0 - Critical | generate_confusion_matrix.py
TASK-INT-01 | Phase 5: Integration | Integration | End-to-End Sorting Pilot Simulation | Simulate 50-egg continuous cycle: load -> index -> capture -> predict -> divert -> sync | System Flowchart | Antigravity / Codex | Backlog | P0 - Critical | test_end_to_end_pilot.py
TASK-INT-02 | Phase 5: Integration | Integration | Offline Network Replay Resilience Test | Cut network; confirm 100% sorting at edge; reconnect and verify bulk replay | AGENTS.md Offline | Antigravity / Codex | Backlog | P0 - Critical | test_offline_network_replay.py
TASK-INT-03 | Phase 5: Integration | Integration | Cradle Position Jam Recovery Test | Simulate mechanical index slip; verify conveyor pauses and resyncs | System Flowchart Node 16 | Antigravity / Codex | Backlog | P1 - High | test_cradle_resync_handler.py
TASK-EVL-01 | Phase 6: Evaluation | Evaluation | Physical Sorting Accuracy Benchmark | Run >= 100 physical duck egg trials to measure sorting accuracy rate | Chapter 1 Objectives | Antigravity | Backlog | P0 - Critical | Physical trial tally sheet
TASK-EVL-02 | Phase 6: Evaluation | Evaluation | System Throughput & Cycle Time Profiling | Measure end-to-end cycle time per egg and throughput (eggs/min) | Chapter 1 Objectives | Antigravity | Backlog | P1 - High | Kinematics benchmark report
TASK-DEF-01 | Phase 7: Defense | Defense Prep | Manuscript Chapter 4 (Results & Discussion) | Draft Chapter 4 using empirical metrics, confusion matrices, latency charts | Chapter 4 | Antigravity | Backlog | P0 - Critical | Manuscript peer review
TASK-DEF-02 | Phase 7: Defense | Defense Prep | Manuscript Chapter 5 (Conclusions & Recommendations) | Summarize findings, answer research questions 1-4, formulate recommendations | Chapter 5 | Antigravity | Backlog | P0 - Critical | Adviser review
TASK-DEF-03 | Phase 7: Defense | Deployment | 1-Click Docker Production Verification | Verify docker-compose up for PostgreSQL 16, FastAPI backend, React dashboard | docker-compose.yml | Antigravity / Codex | Done | P0 - Critical | docker-compose config test
TASK-NEW-FW-APP-01 | Phase 4A: Firmware | Firmware | Unified egg and servo prototype app | CustomTkinter app with independent serial workers, calibration, servo presets, shared controls and explicit simulation | Firmware prototype | Codex | Done | P1 - High | edge/tests/test_firmware_prototype.py + GUI simulation smoke test
TASK-NEW-FW-DET-01 | Phase 4A: Firmware | Firmware | Camera egg detection and optimized operator workspace | Real ONNX classification, stable egg presence, WAL scan recording, manual review, optical events, and bounded background work | Edge prototype | Codex | Done | P1 - High | edge/tests/test_prototype_vision.py and real camera UI smoke test
TASK-NEW-FW-CYCLE-01 | Phase 4A: Firmware | Firmware | Automatic stepper, camera and servo integration cycle | Configurable travel, stationary captures, persisted detection, feedback-driven moves, gate hold, repeat cycles, and manual-review recovery | Edge prototype | Codex | Done | P1 - High | edge/tests/test_prototype_cycle.py, inspection rearm tests and UI smoke check
TASK-NEW-EDGE-CONTROL-01 | Phase 4B: Edge CV | Edge | Dual-board station control and camera defaults | IR-stopped holder tracking; WAL evidence; saved camera/AI defaults. Firmware identification, upload and rig bench validation remain required. | docs/OVALENS_EDGE_STATION_CONTROL.md | Codex | Done | P1 - High | edge/tests/test_station_control.py; native firmware tests; hidden-window UI tests
TASK-NEW-EDGE-UI-POLISH-01 | Development | Edge | Operator typography and visibility | Native Segoe UI; readable status, controls and settings; minimum 1024x720 layout; skip unchanged Tk control and HUD updates. Simulated GUI and before/after status benchmark. | TASK-NEW-EDGE-CONTROL-01 | Operator | Done | High | test_ui_refresh.py; test_startup_config.py; repository verification gate
TASK-NEW-EDGE-DESIGN-02 | Development | Edge | Focused operator design with impeccable | Single record panel; count rows; restrained semantic colour; camera empty state; primary versus secondary actions. Preserve cached refreshes and minimum-size review controls. | TASK-NEW-EDGE-CONTROL-01 | Operator | Done | High | test_ui_refresh.py; test_startup_config.py; repository verification gate
TASK-NEW-EDGE-3BOARD-01 | Phase 4B: Edge CV | Edge CV | Three-board candling integration | Versioned discovery; hardware pause; fresh capture; WAL evidence; position-tracked gates; manual review and recovery. Firmware upload, intended model and physical acceptance remain separately required. | docs/EDGE_THREE_BOARD_IMPLEMENTATION.md | Codex | Done | P1 - High | 50-egg worker simulation; native firmware tests; ESP32 builds; repository verification gate
TASK-NEW-EDGE-SETUP-01 | Phase 4B: Edge CV | Edge CV | Simple default station setup | Remember COM5 stepper, COM7 servo + IR and COM9 light; role detection; main-screen empty-conveyor preparation; cancellable background setup. | docs/EDGE_THREE_BOARD_IMPLEMENTATION.md | Codex | Done | P1 - High | Transport, persistence, cancellation and native GUI tests; repository quality gate; no hardware access
TASK-NEW-EDGE-RUNTIME-01 | Phase 4B: Edge CV | Edge CV | Select project Python at launch | Prefer .venv before dependency imports; double-click Windows launcher; hardware-free runtime check; avoid serial package collision. | edge/README.md | Codex | Done | P1 - High | Interpreter bootstrap unit tests; real global-to-venv import check; repository quality gate
TASK-NEW-FW-INSTALL-01 | Phase 5: Firmware | Firmware | Install three-board v3 firmware | Explicit user approval with empty conveyor; identify old firmware; rebuild and upload COM5/7/9; verify flash hashes, v3 roles and paused/lamp-off telemetry. Physical sorting remains untested. | docs/EDGE_THREE_BOARD_IMPLEMENTATION.md | Codex | Done | P1 - High | Three ESP32 builds; three verified uploads; actual application discovery and boot telemetry